## Sheet1
|  |  |  | Raised week commencing |  | Action for | status
Local authority area | Issue type | Issue details | Action taken to date |  | Action
Scottish Borders Council | Scottish Living Wage | The council is arguing the uplift is non- consolidated. This means that next year's hourly rate will be based on the 19-20 rate, not the 20-21 rate. Providers cannot give a 1 year only uplift to staff. | COSLA has raised with Borders, awaiting response from them. | 2020-07-06 | Escalate to SG so they can provide assurances to the local authority area. | COSLA
Scottish Borders Council | Scottish Living Wage | The council has informed some providers that their uplift will be 'capped' at 2% not the 3.3% | COSLA has raised with Borders, awaiting response from them. | 2020-07-06 | raise with the local authority | COSLA
Moray Council | Scottish Living Wage | The council has informed providers that the 3.3% uplift only applies to the staffing costs component of spot and block contracts. | Moray confirmed approach of parity will be taken between contracts - letter should be issued shortly | 2020-07-06 | raise with the local authority | COSLA
City of Edinburgh Council | Scottish Living Wage | 3.3% not provided to housing support services despite these being noted as in scope in the s.16 of the COSLA commissioning guidance. Arguing does not apply as not delegated to the IA | COSLA raised with SG/SG housing- awaiting feedback. | 2020-07-06 | Escalate to SG as national issue related to variation in delegation of housing support to IJBS | COSLA
National | Scottish Living Wage | 3.3% not provided to housing support services despite these being noted as in scope in the s.16 of the COSLA commissioning guidance. Arguing does not apply as not delegated to the IA | COSLA raised with SG/SG housing- awaiting feedback. | 2020-07-06 | Escalate to SG as national issue related to variation in delegation of housing support to IJBS | COSLA
East Dunbartonshire Council | COVID-19 related costs | Council requiring 3 day turnaround for COVID-19 related costs information. Info required is very detailed including individual invoices | Provider has queried with council then passed to CCPS. | 2020-07-06 | raise with the local authority | COSLA
Aberdeen City Council | COVID-19 related costs | Council process for claiming changing frequently, provider considers information required to be disproportionate | Provider and council are in discussions on this- no action for COSLA and other partners just to be aware. | 2020-07-06 | N/A | N/A
City of Edinburgh Council | Scottish Living Wage | Council wrote again to providers (describing them as 'contractors') stating there will be no 3.3% uplift unless and until they have agreed their disputed funding with SG | Providers have attempted to resolve locally. | 2020-07-06 | raise with SG/communication back to providers on this issue | Dee
Fife Council | Scottish Living Wage | Prior to the announceement by the Cabinet Secretary Fife had offered 2% to their PSP members. Council has not informed PSP providers whether this will be revised upt to 3.3% following the commitment from SG. | Providers have attempted to resolve locally. | 2020-07-06 | Escalate to SG as national issue related to variation in delegation of housing support to IJBS | Dee
City of Edinburgh Council | COVID-19 related costs | CEC has stated that care homes will be 'prioritised' for reimbursement of COVID-19 related costs. Providers concerned that given the limits to the local funding that they will not receive funding for legitimate costs. | none | 2020-07-06 | raise with the local authority | COSLA
Aberdeenshire Council | Scottish Living Wage | Provider has been told their uplift will be capped at 3% due to 'being more expensive than others on the framework' | none | 2020-07-06 | raise with the local authority | COSLA
Midlothian Council | Scottish Living Wage | No uplift awarded | none | 2020-07-06 | Midlothian have confirmed uplift letters sent with 3.3% increase. Waiting for a few providers to sign contracts then payment will be made - Dee can you check with provider? | COSLA
Highland Council | COVID-19 related costs | 7 page form to complete. Providers required to evidence they have sought donations (!!) to meet PPE costs prior to claiming through the COVID-19 related costs process | none | 2020-07-06
Scottish Borders Council | Scottish Living Wage | Council has proposed two different rates (and uplifts) for sleepovers in their SLW uplift letter | none | 2020-07-06 | raise with the local authority | COSLA
Falkirk Council | Scottish Living Wage | 3.3% not provided to housing support services despite these being noted as in scope in the s.16 of the COSLA commissioning guidance. Arguing does not apply as not delegated to the IA | none | 2020-07-06 | Escalate to SG as national issue related to variation in delegation of housing support to IJBS
Angus Council | Scottish Living Wage | Correspondence recently appears to signal that Angus believes the uplift to be non- consolidated. " I would like to advise, however, that at this time the ‘Fair Cost of Care’ rates which were previously communicated to you will remain as the benchmark rate for any uplift in 2021/22 (ie Urban - £18.31, Rural 1 - £23.33, Rural 2 - £36.47), unless we are advised differently by Scottish Government. | none | 2020-07-06 | raise with SG re commitment on future funding | COSLA
North Ayrshire Council | COVID-19 related costs | paying only 24 hours after cancellation, and there is rigorous ECM | written to NAC 8 May, no response. confirmed still an active issue with providers and ISL on 25/06 | 2020-07-06 | Scottish Care to confirm whether provider has submitted claim
North Ayrshire Council | COVID-19 related costs | information re how to claim distributed. Encouraged to claim during provider forum. Provider reported happy with payment made. | no action required | 2020-07-06 | N/A |  | completed
East Ayrshire Council | COVID-19 related costs | Information re how to claim distributed. Encouraged to claim during Forum | no action required. | 2020-07-06 | N/A |  | completed
North Lanarkshire Council | COVID-19 related costs | Care Home Providers return additional cost forms to Partnership (?frequency) | Waiting on further information on payment timescales | 2020-07-06
Fife Council | COVID-19 related costs | The average period used for calculating under occupancy felt to be restrictive to and not reflect full year occupancy targets | Monitoring payment processes and time periods | 2020-07-06 | Scottish Care to check whether approach is different from agreement in principles
Dundee City Council | COVID-19 related costs | Information came quite late as to how to apply. Claims now being made and paid out upon. Fair Work-Living wage letters not yest circulated | Monitoring payment processes and time periods. Established connections with CFO to resolve any issues. | 2020-07-06 | Dundee in discussion with SG re living wage
Aberdeenshire Council | COVID-19 related costs | Claim form submitted no reply | Aberdeenshire has not responded. When I contacted 14 days after submission the response was that they would be in contact once they had something to let me know about.Have been contacted following this and still no reply .Contacted 06/07/20 to be advised that it will be at least another 3 weeks before Angus HSCP will be able to respond to supporting info submitted . | 2020-07-06
| COVID-19 related costs | Claim form submitted but not reviewed |  | 2020-07-06
Moray Council | COVID-19 related costs | No procedure in place ,procedure promised |  | 2020-07-06 | COSLA to contact
Other | COVID-19 related costs | 4 Homes in Aberdeen claim sumbmitted 24th not reviewed |  | 2020-07-06
Glasgow City Council | COVID-19 related costs | Claim form submitted but not reviewed |  | 2020-07-06
Other | COVID-19 related costs | Claim form submitted but not reviewed by NHS Highland |  | 2020-07-06
Scottish Borders Council | COVID-19 related costs | No procedure in place ,procedure promised, most recent communication indicated that funding would not be avalible | Scottish Borders has not responded to issues raised at meeting, follow up emails, no official channel to access funding | 2020-07-06 | COSLA to contact
Scottish Borders Council | Supplier Relief/payment on plan | Concern around access plans to replace staff folowing an out break. 14 volunteer's in place to cover for 1200 staff. No clarity around how replacment staff will be accessed, no induction process for volunteers. | Scottish Borders has not responded to issues raised at meeting, other than to advise that they have 14 volunteers in place | 2020-07-06 | COSLA to contact
Scottish Borders Council | COVID-19 related costs | Additional costs arising from testing, time taken to complete tests is significant. Additional costs preparing for, supporting and folowing visits | Scottish Borders has not responded to issues raised at meeting, follow up emails, no official channel to access funding | 2020-07-06 | COSLA to check with SG re commitment to testing
City of Edinburgh Council | COVID-19 related costs |  | Any issues identified escalated to command centre or appropriate person always a response | 2020-07-06 |  |  | No action required
City of Edinburgh Council | COVID-19 related costs |  | Sustainability template out to care home providers will go out to care at home providers in 2/52 payment will take place within a three week period however where there are financial pressures payment will be made immediately | 2020-07-06 |  |  | No action required
City of Edinburgh Council | COVID-19 related costs |  | still an issue to be resolved with the 3.3% uplift still not redolved Edinburgh along with 5 other partnershps in talk with SG | 2020-07-06 | Edinburgh in discussion with SG
West Lothian Council | COVID-19 related costs | West Lothian circulated information by email to all providers on 17th March inviting claims for Covid related additional expenses. Feedback from providers indicates that payments have already been made | Original email from W.L. re-circulated by I.S.L. Provider's attention drawn to offer of paid expenses at Forums and Branch meetings. Continue to monitor feedback from providers. | 2020-07-06 |  |  | No action required
Moray Council | COVID-19 related costs | No template or guidance in place for providers to reclaim costs | Several contacts requesting guidlines or clarity | 2020-07-06
Moray Council | COVID-19 related costs | length of time being taken to recover cost now beyond 6/7 weeks | Several contacts requesting guidlines or clarity, confirmation of payment | 2020-07-06
Moray Council | COVID-19 related costs | No template or guidance in place for providers to reclaim costs of room vacancies | Several contacts requesting guidlines or clarity | 2020-07-06
Moray Council | COVID-19 related costs | Concerns relating to the above, that the current funding allocation will be used up prior to the providers costs being met | Several contacts requesting guidlines or clarity | 2020-07-06
Angus Council | COVID-19 related costs | Claim forms submitted no payments received |  | 2020-07-10
Aberdeen City Council | COVID-19 related costs | Claim form submitted but not reviewed |  | 2020-07-10
Fife Council | COVID-19 related costs | CAH Template not issued |  | 2020-07-10
South Lanarkshire | COVID-19 related costs | Claim form submitted but not reviewed |  | 2020-07-10
North Lanarkshire Council | COVID-19 related costs | Told payments next week |  | 2020-07-10
Dundee City Council | COVID-19 related costs | Claim form submitted but not reviewed |  | 2020-07-10